## Sheet1
Responsible | RACI Matrix
Accountable
Consulted
Informed
Project Tasks | CEO | Project Manager/Office | Course Administrator | Course Coordinator | Infrastructure & Resource Group | Finance Manager
Develop project charter | R | A | I | I | I | I
Define project scope | R | A | I | I | I | I
Develop project plan | R | A | I | C | I | I
Secure project resources | A | I | I | C | C | R
Develop project budget | R | A | I | C | C | R
Conduct project risk assessment | R | A | I | C | C | R
Assign project team roles and responsibilities | A | A | I | C | I | I
Conduct project team meetings | I | A | I | C | I | I
Monitor project progress | R | A | I | I | I | C
Communicate project status to stakeholders | R | A | I | I | I | C
Resolve project issues and conflicts | R | A | C | I | I | I
Approve project deliverables | R | A | C | R | I | I
Close out project | R | A | I | I | I | I